## Sheet1
Visitor Registration System Project Timeline
Deliverable | Expected | Delivered
Planning and Design Stage
Project Purpose & Requirements | 2021-09-22 | 2021-09-22
Project Work Flow | 2021-09-24 | 2021-09-24
DB Schema | 2021-09-27 | 2021-09-27
Front End and UI
Wireframes | 2021-09-28 | 2021-09-28
Working app Front End | 2021-10-15
Testing & Revisions | 2021-10-17
Back End and API
Database | 2021-10-23
Server Setup | 2021-10-27
API Configuration | 2021-10-29
Testing | 2021-11-05
Launch and Post launch Maintenance & Debugging
Soft Launch
Maintenance & Debugging